## Sheet1
Priority #1
8. Community support and health services
Aspect | Initiative | Priority | Planning Horizon | Convener/Core Group | Community Engagement | Timeline | Cost & Resources | Follow up Measurement | Status
Community Support | Connect local caterers, IH and Meals on Wheels recipients | High | Short | Local businesses/IH/caregivers | AFCP | Fall 2014 | Market-rate meals program | Satisfaction with ‘meals on wheels’-type programs | Under review
Community Support | Age Friendly Business Program | High | Medium | Kicking Horse Chamber of Commerce | AFCP | Fall 2014 | Staff time | Number of “Age Friendly Businesses” | Under review
Community Support | Seniors/Older Adult Coordinator | Moderate | Medium | GCRS/COTR/CBAL | AFCP, Community Coordination – Seniors Groups Meetings | Fall 2014 | Staff wages | Support for Golden’s older adults | To be proposed
Community Support | Inventory Older Adult Programs | Moderate | Long | TBD | AFCP | 2015 | Staff wages, publishing costs (print, web) | Program participation | To be proposed
Priority #2
3. Housing Services
Aspect | Initiative | Priority | Planning Horizon | Convener/Core Group | Community Engagement | Timeline | Cost & Resources | Follow up Measurement | Status
Long term residential care | New long term residential units | High (Importance: 4.12) | Long | Interior Health | IH data; AFCP survey | Ongoing | Undetermined; IH funding | Understanding of actual demand, resources and next steps | To be proposed
Housing Supply & Needs Analysis | Local government’s role in housing communication | High (Importance range: 3.54 – 4.03) | Short | Town of Golden/ Staff | ToG Housing Committee; AFCP survey | Ongoing | Minimal; ToG Staff | Understanding of actual demand, resources and next steps | To be proposed
Shared housing “match-up” program | Housing “match up” program | Moderate | Medium | TBD | AFCP survey | Ongoing | Coordination; New Horizons grant, CBT Community Development Program grant | Waiting list for independent living spaces; number of participants “matched” | To be proposed
Housing Support | Housing Support Business Promotion (cleaning, home maintenance, yard work, snow clearing, computer maintenance, etc.) | Low | Short | KHCCC | AFCP survey | Seasonal | Coordination and promotion; training from Age Friendly Business Canada | Satisfaction with local services; ability to age in place longer | To be proposed
Housing Support | Volunteer Housing Support Programs | Low | Medium | TBD | AFCP survey | Ongoing | Coordination, communication, follow up; New Horizons, Plan H, etc. | Matched participants; satisfaction with program | To be proposed
Priority #3
2. Transportation
Aspect | Initiative | Priority | Planning Horizon | Convener/Core Group | Community Engagement | Timeline | Cost & Resources | Follow up Measurement | Status
Sidewalk condition and availability | Increase ‘sidewalk budget’ | High (AFCP Gap: 0.97) | Short | Town of Golden/ Council | OCP | Every summer | Tax revenue and infrastructure grants | Importance & satisfaction of Town of Golden services | To be proposed
Sidewalk snow and ice clearing | Promote ‘seniors snow clearing program’ | High (AFCP Gap: 0.95) | Short | Town of Golden/ Ops Staff | Town of Golden annual survey | Every winter | Creation, administration and summary of annual survey | Importance & satisfaction of Town of Golden services | To be proposed
Delivery services | Support businesses providing options (prescriptions, food delivery; companionship; driver training). | High | Short | Kicking Horse Chamber of Commerce | AFCP survey | Fall | Borne by the business and customer | Delivery revenue from 50+ market | To be proposed
Weekday service within Golden | Service options: 1. Determine steps necessary to regain Provincial support for public transportation; 2. On-demand service (HandyDART;) 3. Formalize volunteer drivers program (medical and other) | Moderate (Gap: 0.39) | Medium | Town of Golden Planning Dept.; Ministry of Transportation; Interior Health; Seniors Groups | IH data, OCP, AFCP | All year | Tax revenue and infrastructure grants, user fees (10%) | Vitals Signs, Interior Health; residents leaving the community permanently for health reasons | To be proposed
Weekday service within Golden | Transportations service between older adults' homes and community events/programs (e.g. Winter Walking) | Low | Long | Town of Golden, service clubs, activity providers | Town of Golden Staff | All year (especially in winter) | Costs of transportation borne by tax revenue, transit programs, service clubs | Ridership to community events | To be proposed
Active transportation pathways in Golden | Age Friendly Corridor & Active Transportation Mapping | Moderate (Gap: 0.38) | Long | Town of Golden/ Planning Staff (ATC)/ Rotary Club | OCP, AFCP, Active Transportation Committee | Spring 2015 | Accessibility grants, CBT, Rotary, tax revenue, MoT | Active Transportation Audit | To be proposed
Weekday service between Golden and other communities | Approach ‘partners’ (incl. SD#6, biz, other regional groups (RDEK, Invermere Seniors)) | Moderate (Gap: 0.35) | Long | Town of Golden | OCP, AFCP, Recreation Plan | Long | TBD; create plan for sharing of existing resources to increase overall utilization | Ridership; cost recovery through increased asset utilization | To be proposed
Aspect | Initiative | Priority | Planning Horizon | Convener/Core Group | Community Engagement | Timeline | Cost & Resources | Follow up Measurement | Status
Driver training | Encourage driver training courses for those 50+ | Low | Medium | KHCCC, local driver training businesses, COTR, RCMP | AFCP survey | Annually | Costs borne by participants (demand driven) | Number of trained drivers; accident rate for 50+ drivers | To be proposed
Driver assessment | Lobby for improved DriveABLE Assessment service | Low (High importance: 4.18/5; but low probability of change) | Long | MLA | AFCP; letters from MLA | Annually | TBD | Number of local residents losing their driver’s licence | See response from Ministry of Justice in Appendix.
Driver training and awareness | Scooter Rodeo | Low | Long | RCMP and/or Rotary | AFCP survey | Every spring | Promotion, coordination, rodeo course | Number of trained drivers; awareness of scooter driver needs | To be proposed
Priority #4
1. Outdoor spaces and public buildings
Aspect | Initiative | Priority | Planning Horizon | Convener/Core Group | Community Engagement | Timeline | Cost & Resources | Follow up Measurement | Status
Sidewalk condition and availability | Increase ‘sidewalk budget’ | High (AFCP Gap: 1.22) | Short | Town of Golden/ Council | OCP | Every Summer | Tax revenue and infrastructure grants | Importance & satisfaction of Town of Golden services | To be proposed
Sidewalk snow and ice clearing | Promote ‘seniors snow clearing program’ | High (Gap: 0.97) | Short | Town of Golden/ Ops Staff | Town of Golden annual survey | Every winter | Creation, administration and summary of annual survey | Importance & satisfaction of Town of Golden services | To be proposed
Pedestrian crossings | Age Friendly/Accessible Pedestrian Crossings | High (AFCP Gap: 0.96) | Short | Town of Golden Planning Dept.; Ministry of Transportation | Traffic Studies, OCP, AFCP | When traffic necessitates | Tax revenue and infrastructure grants | Importance & satisfaction of Town of Golden services | To be proposed
Snow & ice clearing | Promote “Seniors snow clearing program” | High (AFCP Gap: 0.95) | Short | Town of Golden/ Ops Staff | Town of Golden annual survey | Winter | Time to promote, document feedback | Importance & satisfaction of Town of Golden services | To be proposed
Accessibility and inclusion | Update OCP with a commitment to accessibility and inclusion in the overall mission | High | Medium | Town of Golden/Council | AFCP survey, OCP Update | OCP update 2016 | Included in planned OCP update process | Importance & satisfaction of Town of Golden services | To be proposed
Public Washroom | Public Washroom Promotion – Signage, Opening Hours, Seasonal Dates | Moderate | Short | Town of Golden Staff | AFCP survey | Spring 2015 | RMI funding – signage initiative | Importance & satisfaction of Town of Golden services | To be proposed
Public Buildings | Centralized booking and facility management | Moderate | Medium | Town of Golden, CSRD, SD6, non profits that manage spaces | AFCP survey | Spring 2015 | Software licences, training; | Utilization of public spaces, admin time used by groups | To be proposed
Public Buildings | Install Electric Doors on Public Buildings | Moderate | Medium | Town of Golden Staff | Feedback from Town Staff | Spring 2015 | Accessibility grants, CBT, Rotary, tax revenue | Importance & satisfaction of Town of Golden services | To be proposed
Public Buildings | Hydralic Lift in Pool | Moderate | Medium | Town of Golden Staff | Feedback from Town Staff | Spring 2015 | Accessibility grants, CBT, Rotary, tax revenue | Importance & satisfaction of Town of Golden services | To be proposed
Public Buildings | Wheelchair Lift to Arena Lounge | Moderate | Medium | Town of Golden, CSRD | Feedback from Town Staff | Spring 2015 | Accessibility grants, CBT, Rotary, tax revenue | Utilization of publicly funded facilities | To be proposed
Public Buildings | Joint Use Agreements | Moderate | Long | Town of Golden, CSRD, SD6 | AFCP survey | Spring 2015 | Substantial; savings could be considerable | Utilization of publicly funded facilities; costs to manage publicly owned facilities | To be proposed
Aspect | Initiative | Priority | Planning Horizon | Convener/Core Group | Community Engagement | Timeline | Cost & Resources | Follow up Measurement | Status
Public Buildings Awareness | Public Space Promotion – “Scavenger Hunt/Amazing Race” and “Photo Contest” | Low | Short | Town of Golden Staff | AFCP survey | TBD | Recreation & Operations staff | Importance & satisfaction of Town of Golden services | To be proposed
Public Building s Awareness | Public Space of the Week: | Low | Short | Town of Golden Staff | AFCP survey | TBD | Places chosen are seasonal; a contest to “guess where this photo was taken.” | Importance & satisfaction of Town of Golden services | To be proposed
Snow & ice clearing | Public Sanding Boxing along high foot traffic areas | Low | Short | Town of Golden/ Ops Staff | Completed through OCP | Every Winter | 10 plastic “sanding boxes,’ sand and instructions ($2,500); Tax revenue and infrastructure grants | Measure use of sand. | To be proposed
Sidewalk condition and availability | Increase ToG reserves for ‘Paving, Patching & Sidewalks’ | Low | Medium | Town Council | AFCP | 2015 budget | TBD | Reserve balance for future expense item | To be proposed
Trail condition and availability | Rotary Trail Enhancements | Low | Long | Rotary Club of Golden | AFCP Survey, OCP, Active Transportation Audit | 2014-16 | Fundraising | Active Transportation Audit | To be proposed
Sidewalk condition and availability | Age Friendly Corridor & Active Transportation Mapping | Low | Long | Town of Golden/ Planning Staff (ATC)/ Rotary Club | OCP, AFCP, Active Transportation Committee | Spring 2015 | Accessibility grants, CBT, Rotary, tax revenue, MoT | Active Transportation Audit | To be proposed
Trail condition and availability | Nordic skiing along Rotary Trails | Low | Long | Town of Golden, Golden Nordic Ski Club | AFCP | Winter 2016 | Reduced snow clearing along Rotary Trails | Active Transportation Audit | To be proposed
Priority #5
4. Social Participation
Aspect | Initiative | Priority | Planning Horizon | Convener/Core Group | Community Engagement | Timeline | Cost & Resources | Follow up Measurement | Status
Specialized fitness/wellness programs | Inventory specialized fitness/wellness programs | High (Gap: 0.74) | Short | Town of Golden Recreation Services; KHCCC; Mt.7 Rec Plex Society/users | IH data; AFCP survey | Fall, winter | Undetermined | Understanding of actual demand, resources and next steps | To be proposed
Older adults’ fitness, health and wellness programs | Communication – Improved utilization of Community Calendar – through training and incentives (using inventory above) | Moderate (Gap: 0.53) | Short | KHCCC, Town of Golden | AFCP survey | Fall | Minimal; ToG, KHCCC Staff | Enrollment/participation in older adult programs | To be proposed
Technology training | Smart Phone, tablet and Windows 8 Support through COTR | Moderate (Gap: 0.36) | Short | COTR, CBAL, Golden Seniors | AFCP survey | Ongoing | Undetermined | Number of participants, competency/comfort with technology | In place
Activity promotion | Social Participation promotion at Soup Days | Moderate | Short | Golden Seniors; Town of Golden; KHCCC; COTR | AFCP survey | Fall | Minimal, staff/volunteers to staff desk, promotional materials | Participation rates with promoted activities | To be proposed
Volunteer opportunities | Older adult needs integrated into infrastructure projects (indoor pool) | Moderate | Short | Town of Golden; special interest groups | AFCP survey | Ongoing | Volunteers’ time | Fit and perception of indoor pool proposal with 50+ residents | To be proposed
Art, writing, craft, hobbies and music therapy programs | COTR – Senior Arts Program | Low (Gap: 0.22) | Short | COTR | AFCP survey | Ongoing | TBD | Number of participants, satisfaction | Continuous Improvement
Community Events | Feed events into Community Calendar | Low (Gap: -0.04) | Short | KHCCC | AFCP survey | Ongoing | Minimal | Number of events in Community Calendar, attendance at promoted events | Continuous Improvement
Aspect | Initiative | Priority | Planning Horizon | Convener/Core Group | Community Engagement | Timeline | Cost & Resources | Follow up Measurement | Status
Continuing Education | Certificate, Diploma and Degree Programs | Low (Gap: 0.02) | Long | COTR | AFCP survey | Ongoing | TBD | Number of students, courses enrolled in, programs completed | Continuous Improvement
Community Events | Community Participation Bursary Program for low income adults | Low (Gap: -0.04) | Long | Town of Golden | AFCP survey, Whitetooth Affordable Ski Program | Fall | TBD | Increased participation from low income residents | To be proposed
Social groups | Informal activity-based social groups | Low (Gap: -0.16) | Long | Golden Seniors, Legion, Town of Golden Rec Services | AFCP survey | Ongoing | Status quo | Participation and satisfaction | Continuous Improvement
Games | Games | Low (Gap: -0.21) | Long | Golden Seniors/Royal Canadian Legion | AFCP survey | Ongoing | Status quo | Participation and satisfaction | Continuous Improvement
7. Communication and information
Priority #6
Aspect | Initiative | Priority | Planning Horizon | Convener/Core Group | Community Engagement | Timeline | Cost & Resources | Follow up Measurement | Status
Communication | Community Calendar | High | Short | KHCCC | AFCP | Summer, Fall 2014 | Staff time | Number of events, user groups on monthly calendar | Under review
Information | Community Registration Night | High | Short | Town of Golden | AFCP | 2014-09-01 | Space, advertising, volunteer and staff time | Volunteer participation; public awareness of programs | Ongoing
Communication | Community Collaboration | High | Short | GCRS | Vital Signs | Summer 2014 | Staff time, volunteer participation | Percentage of successful community projects | Under review
Communication | Event Promotion – WOM, Print and Online for all | Moderate | Medium | KHCCC | AFCP | Fall 2014 | Staff time, presentation development | Event attendance | To be proposed
Communication | Non profit list | Moderate | Short | GCRS | AFCP, Community Coordination | Fall 2014 | Staff time, BC Registry Services | Number of active, registered non profit organizations | Awaiting funding
Communication | Technology Training Program | Moderate | Medium | COTR/CBAL | AFCP | Fall 2014 | TBD | Competency and comfort with technology | To be proposed
Information | Local report record keeping | Moderate | Medium | Town of Golden/GAI | AFCP | Fall 2014 | Staff time | Number of inquiries, web clicks, page views | To be proposed
Information | Local report record keeping | Low | Long | Town of Golden/GAI | AFCP | 2015 | Staff time, scanning | Number of recorded local groups | To be proposed
Information | Older adult participation in Indoor Pool project discussion | Low | Long | Town of Golden/volunteer group | AFCP feedback | 2015 | Volunteer time | Integration of older adult needs in next Indoor Pool proposal | To be proposed
Priority #7
5. Respect and social inclusion
Aspect | Initiative | Priority | Planning Horizon | Convener/Core Group | Community Engagement | Timeline | Cost & Resources | Follow up Measurement | Status
Inclusion | Increased promotion and utilization of Welcome Wagon program | High | Short | Welcome Wagon | AFCP | Ongoing | TBD | Increase in “Golden is a welcoming community to be an older adult” rating | To be proposed
Inclusion | Increased promotion of Community Registration Night | High | Short | Town of Golden Rec Services | AFCP | Annual | Specialized messaging to older adult groups and older adults | Volunteer participation; enrollment in programs | To be proposed
Respect | Volunteer Recognition for all volunteers | High | Medium | Town of Golden/Service Clubs | AFCP | Annual | Volunteer recognition event; ~$1,500 | Volunteerism rates | To be proposed
Respect | World/Super Host Customer Service Excellence Training for Volunteers | Moderate | Medium | BCVC, Town of Golden, Tourism Golden | AFCP Survey | Every fall and spring | Host training, logo wear, iPads, signage; New Horizons grant | Volunteer participation; tourist response (Tourism Golden) | To be proposed
Inclusion | Volunteer Development & Management Program | Moderate | Long | Town of Golden, Social Service groups | AFCP Survey | Ongoing | Coordinator, program design, monitoring; grants | Importance & satisfaction of Town of Golden services | To be proposed
Respect | Community Ambassador/ Host Program | Low | Long | BCVC, Town of Golden, Tourism Golden | AFCP Survey | Every fall and spring; special events | RMI funding | Volunteer participation; tourist response (Tourism Golden) | To be proposed
Priority #8
6. Civic participation and employment
Aspect | Initiative | Priority | Planning Horizon | Convener/Core Group | Community Engagement | Timeline | Cost & Resources | Follow up Measurement | Status
Employment | Secure Older Worker Program | High (Satisfaction: 3.5/5) | Short | College of the Rockies | AFCP | Continuous | Service delivery agreement | Importance & satisfaction of employment services | Application under review
Civic Participation | Create Community Coordinator/Developer Role | High | Short | Town of Golden | AFCP/Community Coordination | ASAP | Jointly funded by Town of Golden, CBT, CSRD; CBT CDP and eventually Community-Directed Funds program | Civic and social participation; | In progress (since Dec 2013)
Civic Participation | Community Conversations | Medium | Medium | Town of Golden/Christina Benty/CBT | Community Conversations Series 2013/14 | 2015-01-01 | Facilitation, meeting space rental | Voter participation | To be proposed
Civic Participation | Promotion and recognition of local government volunteers | Medium | Medium | Town of Golden/CSRD | AFCP | 2015-01-01 | Listing and recognition of all local government volunteers, volunteer appreciation event | Volunteer interest, participation | To be proposed
Civic Participation | Volunteer Development and Management | Medium | Medium | Town of Golden | AFCP/Community Coordination | Fall 2014 | Coordinator, process, job descriptions, HR/volunteer management training | Civic participation, social participation | To be proposed
CSRD Fire Suppression | Communicate review of CSRD Fire Services | Low | Long | CSRD/Community Associations | CSRD | TBD | TBD | CSRD resident satisfaction | To be proposed